## WBS & Rencana Kerja
RENCANA KERJA & WBS PEMBUATAN WEBSITE SALON YALIA BEAUTY
Sistem Informasi Reservasi Salon & Home Service (Laravel 13 & Tailwind CSS) • Soft Green Theme
TOTAL TUGAS (WBS) |  | SELESAI (100%) |  | DALAM PROSES |  | TOTAL PROGRESS
No | Kode WBS | Nama Tugas / Modul Sistem | Fase Project | PIC / Role | Durasi | Status | Progress (%)
1 | WBS 1.1 | Analisis Kebutuhan Sistem & User Persona | Fase 1: Perancangan | System Analyst | 2 Hari | Selesai | 100%
2 | WBS 1.2 | Pembuatan Flowchart Manual Booking & Gamifikasi | Fase 1: Perancangan | System Analyst | 3 Hari | Selesai | 100%
3 | WBS 1.3 | Perancangan ERD Pohon Diagrams (15 Entitas) | Fase 1: Perancangan | Database Engineer | 3 Hari | Selesai | 100%
4 | WBS 1.4 | Perancangan DFD Level 0 & DFD Level 1 (Data Stores) | Fase 1: Perancangan | System Analyst | 2 Hari | Selesai | 100%
5 | WBS 2.1 | Penyusunan Design System & Palette (Soft Pink #f472b6) | Fase 2: UI/UX | UI/UX Designer | 2 Hari | Selesai | 100%
6 | WBS 2.2 | Layouting Landing Page & Catalog Treatment | Fase 2: UI/UX | Frontend Dev | 4 Hari | Selesai | 100%
7 | WBS 2.3 | Sistem Komponen Navigation & Responsive Header/Footer | Fase 2: UI/UX | Frontend Dev | 3 Hari | Selesai | 100%
8 | WBS 2.4 | Halaman Admin Dashboard & Panel Manajemen | Fase 2: UI/UX | Frontend Dev | 4 Hari | Selesai | 100%
9 | WBS 3.1 | Setup Laravel 13 Framework & Migrasi Database | Fase 3: Backend | Backend Dev | 2 Hari | Selesai | 100%
10 | WBS 3.2 | Implementasi Eloquent Models & Relasi Database | Fase 3: Backend | Backend Dev | 3 Hari | Selesai | 100%
11 | WBS 3.3 | Fitur Autentikasi Breeze & Google OAuth Integration | Fase 3: Backend | Backend Dev | 3 Hari | Selesai | 100%
12 | WBS 3.4 | Manajemen Treatment, Kategori, & Beautician Profile | Fase 3: Backend | Backend Dev | 3 Hari | Selesai | 100%
13 | WBS 4.1 | Algoritma Perhitungan Slot Jam Availability | Fase 4: Core Engine | Backend Dev | 4 Hari | Selesai | 100%
14 | WBS 4.2 | Fitur Reservasi Salon vs Home Service Radius GPS | Fase 4: Core Engine | Fullstack Dev | 4 Hari | Selesai | 100%
15 | WBS 4.3 | Modul Penugasan Kapster & Beautician Schedule | Fase 4: Core Engine | Backend Dev | 3 Hari | Selesai | 100%
16 | WBS 4.4 | Modul Batal Booking & Reschedule Jadwal Perawatan | Fase 4: Core Engine | Fullstack Dev | 3 Hari | Selesai | 100%
17 | WBS 5.1 | Integrasi Midtrans Payment Gateway (QRIS & Snap) | Fase 5: Integration | Backend Dev | 4 Hari | Selesai | 100%
18 | WBS 5.2 | Webhook Handler Auto Settlement & Status Pembayaran | Fase 5: Integration | Backend Dev | 2 Hari | Selesai | 100%
19 | WBS 5.3 | Sistem Gamifikasi Poin Reward PTS & Tier Loyalty | Fase 5: Integration | Fullstack Dev | 4 Hari | Selesai | 100%
20 | WBS 5.4 | Modul Kupon Voucher Diskon & Check-in Streak | Fase 5: Integration | Fullstack Dev | 3 Hari | Selesai | 100%
21 | WBS 6.1 | Unit Testing & Integration Test Suite (PHPUnit) | Fase 6: Testing | QA Engineer | 3 Hari | Selesai | 100%
22 | WBS 6.2 | Optimalisasi Performance Performa Laravel Octane v2 | Fase 6: Testing | DevOps Engineer | 2 Hari | Selesai | 100%
23 | WBS 6.3 | Keamanan Data, Middleware, & Input Sanitization | Fase 6: Testing | Security Lead | 2 Hari | Selesai | 100%
24 | WBS 6.4 | Final Deployment Staging Server & UAT User Review | Fase 6: Testing | Project Manager | 2 Hari | Selesai | 100%